## LinkedIn Scraper Advancement
Task | Priority | Status | 2022-08-06 | 2022-08-09 | 2022-08-10 | 2022-08-11
Connect to LinkedIn | 1 | Done
Select "Jobs" section | 1 | Done
Type in the search bar | 1 | Done
Get the number of pages | 2 | Done
Launch scraper on a different Thread | 2 | Done
Add a progress bar | 3 | On Hold
Solve the "Not working" pages | 1 | Done
Create Figma file to design | 1 | On Hold
Design UI | 3 | On Progress
Add Scrap and Analyze buttons in left panel Figma | 2 | On Hold
Create a Power BI report with the results | 2 | On Progress
Analyze per text and don't group them, create objects | 1 | Done
Design Power BI with evolution of used terms by months | 2 | On Progress
Keep all the data in the exports for Power Bi for further analysis | 1 | On Progress
Manage GitHub credentials | 1 | Done
Add false accounts to go faster to scrap | 3 | Done
Get contents - attributes as lists | 1 | Done
Style button for next and previous | 3 | Done
Add button execute to the task | 1 | On Progress
Load the different files on the left panel | 1 | On Progress
Create a function to export the current window state in a json file | 1 | On Progress
Add button to delete action | 1 | On Progress
Add button to delete task | 1 | On Progress
Add button to create a new json file | 1 | On Progress
Add button to create a new task | 1 | On Progress
Add button to create a new action | 1 | On Progress
Add the name in front of the action itself in a line edit | 2 | On Progress